## approvals
A01_id | project_id | A01_primary_authority | A02_noc_status | A03_noc_issue_date | A04_building_permit_no | A05_bp_issue_date | A06_bp_expiry_date | A07_completion_cert_no | A08_cc_issue_date | A09_occupation_cert_no | A10_oc_issue_date
1 | PRJ-001 | Dubai Municipality | Approved | 2023-09-15 | BP-2023-456 | 2023-09-15 | 2025-09-15
2 | PRJ-001 | DEWA | Approved | 2023-08-01
3 | PRJ-002 | DM | Approved | 2023-11-15 | BP-2023-789 | 2023-11-15 | 2025-11-15
4 | PRJ-003 | ADM | Pending
5 | PRJ-005 | RAK Municipality | Submitted

## sqlite_sequence
name | seq
permit_sequence | 14
approvals | 5
authority_matrix | 5

## authority_matrix
id | emirate | jurisdiction | master_planning | building_permit | civil_defense | power_water | district_cooling | notes
1 | Dubai | DM-Mainland | DM Planning | DM Building Permit | Civil Defence | DEWA | Tabreed | Main authority
2 | Dubai | Trakhees | DM Planning | DM Building Permit | Civil Defence | DEWA | Tabreed | PCFC cluster
3 | Abu Dhabi | ADM | ADM Planning | ADM Building Permit | Civil Defence | ADDC | ADCDA | Island authority
4 | Sharjah | SHA | SHA Planning | SHA Building Permit | Civil Defence | SEWA |  | Municipality
5 | Ras Al Khaimah | RAK | RAK Planning | RAK Building Permit | Civil Defence | RAK EA |  | Municipality

## permit_sequence
id | step_number | permit_name | min_days | max_days | avg_days | min_cost_aed | max_cost_aed | avg_cost_aed | authority | notes
1 | 1 | Land Title Deed | 7 | 14 | 10 | 0 | 0 | 0 | DLD
2 | 2 | Land NOC from DLD | 5 | 10 | 7 | 500 | 1000 | 750 | DLD
3 | 3 | Initial Planning Approval | 14 | 28 | 21 | 2000 | 5000 | 3500 | DM/DDA
4 | 4 | Environmental NOC | 30 | 60 | 45 | 10000 | 50000 | 30000 | DM/EPDA
5 | 5 | Geotechnical Report | 14 | 28 | 21 | 15000 | 100000 | 57500 | DM
6 | 6 | RTA NOC | 30 | 60 | 45 | 5000 | 50000 | 27500 | RTA
7 | 7 | Civil Defense NOC | 14 | 28 | 21 | 2000 | 10000 | 6000 | DCD
8 | 8 | DEWA Connection | 30 | 90 | 60 | 10000 | 500000 | 255000 | DEWA
9 | 9 | Building Permit | 30 | 60 | 45 | 0 | 0 | 0 | DM/DDA/Trakhees
10 | 10 | District Cooling NOC | 30 | 60 | 45 | 50000 | 500000 | 275000 | Empower/Tabreed
11 | 11 | Telecom NOC | 14 | 28 | 21 | 5000 | 50000 | 27500 | du/Etisalat
12 | 12 | SIRA Security Approval | 14 | 28 | 21 | 3000 | 20000 | 11500 | SIRA
13 | 13 | Completion Certificate | 14 | 28 | 21 | 1000 | 5000 | 3000 | DM
14 | 14 | Occupancy Certificate | 7 | 14 | 10 | 500 | 2000 | 1250 | DM

## authority_matrix_raw
EMIRATE | JURISDICTION | MASTER_PLANNING | BUILDING_PERMIT | CIVIL_DEFENSE | POWER_WATER | DISTRICT_COOLING | NOTES
Dubai | Dubai Municipality (DM) | DM | DM | DCD | DEWA | Empower | Mainland
Dubai | DDA (DIEZ) | DDA | DDA | DCD | DEWA | Empower/Other | Creative/Tech zones
Dubai | Trakhees (PCFC) | Trakhees | Trakhees | DCD | DEWA | Empower/Other | Ports/Freezone areas
Abu Dhabi | DMT (Mainland) | DMT | DMT | ADCDA | ADPower/AADC | Tabreed | Mainland

## mv_auth_matrix
id | emirate | authority | project_type | typology | requirements | processing_days | fees_aed | notes | pre_requisites | renewal_period_months | inspection_required | digital_portal
1 | DXB | Dubai Municipality (DM) | RESI | Villa (≤800 m²) | Building permit, NOC | 30 | 5000 | Standard residential approval |  | 12 | Yes
2 | DXB | DEWA | RESI | Villa (≤800 m²) | Electricity connection | 15 | 2000 | Standard connection |  | 12 | Yes
3 | AUH | Abu Dhabi Municipality | COMM | Office | Commercial permit | 45 | 10000 | Commercial building approval |  | 12 | Yes
4 | SHJ | SEWA | RESI | Townhouse | Utilities connection | 20 | 3000 | Water and electricity |  | 12 | Yes