## schedule_data
T01_id | project_id | T01_start_date | T02_design_complete | T03_permit_issued | T04_construction_start | T05_construction_end | T06_handover_date | T07_duration_months | T08_current_phase
1 | PRJ-001 | 2023-01-01 | 2023-06-30 | 2023-09-15 | 2023-11-01 | 2026-06-30 | 2026-09-30 | 36 | Construction
2 | PRJ-002 | 2023-03-01 | 2023-08-30 | 2023-11-15 | 2024-01-15 | 2026-12-31 | 2027-03-31 | 39 | Construction
3 | PRJ-003 | 2024-06-01 | 2024-12-31 | 2025-03-01 | 2025-05-01 | 2026-03-31 | 2026-06-30 | 24 | Design
4 | PRJ-004 | 2025-01-01 | 2025-06-30 | 2025-09-01 | 2025-11-01 | 2027-06-30 | 2027-09-30 | 33 | Feasibility
5 | PRJ-005 | 2024-01-01 | 2024-06-30 | 2024-09-01 | 2024-11-01 | 2026-09-30 | 2026-12-31 | 30 | Construction

## sqlite_sequence
name | seq
wbs_activities | 23
schedule_data | 5

## wbs_activities
id | project_id | phase_id | phase_name | activity_id | activity_name | duration_days | start_date | end_date | is_critical | predecessor | resource_type | planned_pct | actual_pct
1 |  | 1 | Enabling Works | 101 | Site Clearance & Mobilization | 14 |  |  | 0 |  | Labour | 0 | 0
2 |  | 1 | Enabling Works | 102 | Shoring Installation | 28 |  |  | 0 | 101 | Equipment | 0 | 0
3 |  | 1 | Enabling Works | 103 | Excavation | 21 |  |  | 0 | 102 | Equipment | 0 | 0
4 |  | 1 | Enabling Works | 104 | Pile Foundations | 45 |  |  | 1 | 103 | Piling | 0 | 0
5 |  | 2 | Substructure | 201 | Raft Foundation | 30 |  |  | 1 | 104 | Concrete | 0 | 0
6 |  | 2 | Substructure | 202 | Basement Walls | 21 |  |  | 0 | 201 | Concrete | 0 | 0
7 |  | 2 | Substructure | 203 | Basement Slab | 14 |  |  | 0 | 202 | Concrete | 0 | 0
8 |  | 3 | Superstructure | 301 | Ground Floor Slab | 10 |  |  | 0 | 203 | Concrete | 0 | 0
9 |  | 3 | Superstructure | 302 | Typical Floor Cycle | 7 |  |  | 1 | 301 | Concrete | 0 | 0
10 |  | 3 | Superstructure | 303 | Structure Complete | 0 |  |  | 1 | 302 | Concrete | 0 | 0
11 |  | 4 | MEP Rough-in | 401 | MEP First Fix | 60 |  |  | 0 | 301 | MEP | 0 | 0
12 |  | 4 | MEP Rough-in | 402 | MEP Second Fix | 45 |  |  | 0 | 401 | MEP | 0 | 0
13 |  | 5 | Finishes | 501 | Internal Plastering | 30 |  |  | 0 | 401 | Finishes | 0 | 0
14 |  | 5 | Finishes | 502 | Tiling & Flooring | 40 |  |  | 0 | 501 | Finishes | 0 | 0
15 |  | 5 | Finishes | 503 | Painting & Decoration | 25 |  |  | 0 | 502 | Finishes | 0 | 0
16 |  | 6 | External Works | 601 | Facade Installation | 90 |  |  | 0 | 303 | Specialist | 0 | 0
17 |  | 6 | External Works | 602 | Landscaping | 30 |  |  | 0 | 601 | Labour | 0 | 0
18 |  | 7 | Commissioning | 701 | MEP Testing & Commissioning | 30 |  |  | 0 | 402 | MEP | 0 | 0
19 |  | 7 | Commissioning | 702 | Fire Life Safety | 21 |  |  | 0 | 701 | Specialist | 0 | 0
20 |  | 7 | Commissioning | 703 | Final Inspection | 14 |  |  | 0 | 702 | Inspection | 0 | 0
21 |  | 8 | Handover | 801 | Snagging & Rectification | 21 |  |  | 0 | 703 | All | 0 | 0
22 |  | 8 | Handover | 802 | Completion Certificate | 14 |  |  | 0 | 801 | Authority | 0 | 0
23 |  | 8 | Handover | 803 | Occupancy Certificate | 7 |  |  | 0 | 802 | Authority | 0 | 0

## mv_permit_sequence
id | permit_name | authority | avg_days | avg_cost_aed | dependencies