## sustainability
id | project_id | sustainability_id | leed_certification_goal | estidama_pearl_target | dubai_green_score | energy_consumption_target | water_consumption_target | recycled_material_target | renewable_energy_pct | carbon_footprint_target | waste_diversion_target | green_roof_area_pct | ev_charging_stations | green_materials_pct | operational_carbon_reduction | embodied_carbon_reduction
1 | PRJ-001 | SUS-001 | Gold | 2 Pearl | 2 | 120 | 180 | 30 | 15 | 2.5 | 70 | 25 | 10 | 40 | 20 | 15
2 | PRJ-002 | SUS-002 | Silver | 1 Pearl | 1 | 140 | 200 | 25 | 10 | 3 | 60 | 20 | 8 | 35 | 15 | 12
3 | PRJ-003 | SUS-003 | Certified | 1 Pearl | 0 | 150 | 220 | 20 | 5 | 3.5 | 50 | 15 | 6 | 30 | 10 | 10

## sqlite_sequence
name | seq
risk_register | 10
sustainability | 3
quality_master | 2
bim_master | 2
omm_master | 2

## quality_master
id | project_id | quality_id | quality_plan_id | inspection_test_plan_id | material_approval_status | shop_drawing_status | testing_requirement | inspection_hold_point | quality_control_checklist | non_conformance_report_id | corrective_action_id | quality_kpi_measurement | customer_satisfaction_index | defect_density | rework_cost_aed | first_pass_yield | quality_management_system | accreditation_certification | regulatory_compliance_status
1 | PRJ-001 | QM-001 | QP-001 | ITP-001 | Approved | Submitted | Required | Hold Point | Active | NCR-001 | CA-001 | 95 | 4.2 | 2.1 | 50000 | 92 | ISO 9001:2015 | ISO 17025 | Compliant
2 | PRJ-002 | QM-002 | QP-002 | ITP-002 | Approved | Submitted | Required | Witness Point | Active |  |  | 90 | 3.8 | 2.5 | 35000 | 88 | ISO 9001:2015 |  | Compliant

## risk_register
id | project_id | risk_id | risk_category | risk_description | probability_pct | impact_level | risk_score | risk_owner | risk_response_strategy | mitigation_action | contingency_plan | trigger_indicator | risk_status | risk_budget_aed
1 |  | R101 | Schedule/Claims | Artificially inflated schedule buffer masks delays | 60 | 80 | 48 |  |  | Maintain transparent schedules; conduct independent reviews
2 |  | R102 | Environmental | Productivity loss due to extreme summer temperatures | 80 | 60 | 48 |  |  | Schedule outdoor work Oct-Apr; provide cooling stations
3 |  | R103 | Supply Chain | Delays at port or customs for imported materials | 60 | 70 | 42 |  |  | Maintain buffer stock; pre-approve suppliers; source locally
4 |  | R104 | Regulatory | Longer than expected time for NOCs and permits | 50 | 60 | 30 |  |  | Ensure complete submissions; engage dedicated permits manager
5 |  | R105 | Technical | Soil conditions differ from initial report | 40 | 90 | 36 |  |  | Comprehensive soil investigation; contingency in foundation budget
6 |  | R106 | Financial | Steel/concrete price increases during construction | 55 | 65 | 36 |  |  | Lock prices in contracts; include escalation clause
7 |  | R107 | Resource | Difficulty in securing skilled labor | 45 | 70 | 32 |  |  | Pre-qualify multiple subcontractors; early mobilization
8 |  | R108 | Design | Client-initiated changes after construction starts | 35 | 85 | 30 |  |  | Firm scope freeze; change order procedures
9 |  | R109 | Financial | Exchange rate changes affecting imported materials | 40 | 55 | 22 |  |  | Hedge currency risk; local sourcing strategy
10 |  | R110 | Force Majeure | Work restrictions due to health emergencies | 20 | 90 | 18 |  |  | Business continuity plan; remote work protocols

## bim_master
id | project_id | bim_id | bim_uses | lod_requirement | model_responsibility_matrix | cde_platform | clash_detection_protocol | quantity_takeoff_method | simulation_4d_required | costing_5d_required | asset_information_requirement | co_bie_deliverable | digital_twin_requirement | software_platforms | bim_standards_compliance
1 | PRJ-001 | BIM-001 | Design,Coordination,4D,5D | LOD 350 | Full Matrix | BIM 360 | Weekly Clash Detection | Automated QTO | 1 | 1 | Required | Yes | Phase 2 | Revit,Navisworks | ISO 19650
2 | PRJ-002 | BIM-002 | Design,Coordination | LOD 300 | Partial Matrix | BIM 360 | Monthly Clash Detection | Manual QTO | 1 | 0 | Required | No | Phase 1 | Revit | ISO 19650

## omm_master
id | project_id | omm_id | preventive_maintenance_schedule | spare_parts_inventory | warranty_management | service_provider_contracts | facility_management_system | energy_management_system | life_cycle_cost_analysis | replacement_schedule | operational_budget_aed_year | maintenance_staffing | handover_requirements | as_built_documentation
1 | PRJ-001 | OMM-001 | Monthly HVAC, Quarterly Electrical | Yes | 5-year warranty | Annual Contract | CAFM System | BMS Integration | 30-year LCA | Per Manual | 2500000 | 15 FM Staff | Full Package | Required
2 | PRJ-002 | OMM-002 | Quarterly All Systems | Yes | 3-year warranty | Annual Contract | CAFM System |  | 25-year LCA | Per Manual | 1800000 | 10 FM Staff | Full Package | Required

## risks_catalog_raw
RISK_ID | RISK_NAME | CATEGORY | DESCRIPTION | DEFAULT_PROBABILITY | DEFAULT_IMPACT | STANDARD_MITIGATION
R101 | False Float in Schedule | Schedule/Claims | Artificially inflated schedule buffer masks delays, hurting genuine EOT claims. | 0.6 | 0.8 | Maintain transparent schedules; conduct independent schedule reviews.
R102 | Weather Delays (Summer Heat) | Environmental | Productivity loss and work stoppages due to extreme summer temperatures. | 0.8 | 0.6 | Schedule critical outdoor work during cooler months; provide adequate cooling.
R103 | Material Import Delays | Supply Chain | Delays at port or customs for internationally sourced materials. | 0.6 | 0.7 | Maintain buffer stock; pre-approve suppliers; source locally where possible.
R104 | Municipality Approval Delays | Regulatory | Longer than expected time to receive NOCs and building permits. | 0.5 | 0.6 | Ensure complete and accurate submissions; engage a dedicated permits manager.
R105 | Unexpected Geotechnical Conditions | Technical | Soil conditions differ from the initial report, requiring design changes. | 0.4 | 0.9 | Perform comprehensive soil investigation; include contingency in foundation budget.

## mv_risk_register
risk_id | description | category | probability | impact | score | owner | mitigation | status
RSK-MV-001 | Foundation soil discrepancy | Technical | 3 | 5 | 15 | Geotech Engineer | Additional boring | Open
RSK-MV-002 | Material price escalation | Commercial | 4 | 4 | 16 | QS | Fixed-price contracts | Open
RSK-MV-003 | Permit delay | Regulatory | 3 | 4 | 12 | PM | Pre-application meetings | Open
RSK-MV-004 | Labor shortage | Resource | 4 | 3 | 12 | Contractor | Multi-labor agreements | Open
RSK-MV-005 | Design change | Design | 3 | 4 | 12 | Design Manager | Freeze design at 90% DD | Open